eMarketSelect

# Employee Management System

Simple Production Build Plan

One system. Clear phases. No duplicate data or duplicated business logic.

Current position The Supabase backend foundation is already prepared. The real Next.js application has not been built yet. The next development work is PHASE 1: Project Foundation.

How to read this document The phases are not separate applications. We are building one EMS. Each phase adds the next working layer to the same application.

PROJECT STATUS

# 1. What is already completed?

The work below is preparation completed before the application build starts. We do not repeat it in Phase 1.

| Status | Area | Meaning |
| --- | --- | --- |
| DONE | EMS prototype | Main screens and workflows are defined. |
| DONE | Requirements | Scrum, attendance, presence, requests, roles and privacy rules are defined. |
| DONE | Supabase | Project is connected and working. |
| DONE | Database | 29 normalized production tables are created. |
| DONE | Security | RLS is enabled on all public tables; latest security check reported 0 issues. |
| DONE | Configuration | 7 departments, 4 schedules, 5 leave types, company defaults and realtime tables are prepared. |
| DONE | Admin profiles | EMS-001 and EMS-DEMO-001 profiles are provisioned. |
| NEXT | Demo Auth user | Create the demo password user in Supabase Authentication. |
| NOT STARTED | Next.js app | The real frontend application code has not been built yet. |

What this means Backend preparation is ready enough to begin the real app. Phase 1 does not rebuild Supabase; it creates the Next.js application and connects it to the backend already in place.

HOW THE BUILD WORKS

# 2. How the phases behave

We build one EMS in a fixed order. Each phase stays in the same project and becomes the foundation for the next phase.

| PHASE 1 Foundation | PHASE 2 Authentication | PHASE 3 Employees |
| --- | --- | --- |
| PHASE 4 My Day & Scrum | PHASE 5 Attendance & Presence | PHASE 6 Requests |
| PHASE 7 Management & Reports | PHASE 8 Admin & Audit | PHASE 9 QA & Pilot |

Simple example Phase 1 creates the app shell. Phase 2 adds login to that same app. Phase 3 adds employees. Phase 4 adds My Day and Scrum. Later phases keep using the same user profiles, database and permission model.

## Rule for every phase

Build only the scope of the current phase.

Connect it to the existing Supabase database instead of making temporary duplicate data.

Test UI, database behavior and permissions before moving forward.

Fix blocking issues before starting the next phase.

CURRENT DEVELOPMENT PHASE

PHASE 1  Project Foundation

| CURRENT / NEXT | Create the real application structure that every later EMS feature will use. |
| --- | --- |

What we build

Initialize Next.js + TypeScript in the Demo-EMS- GitHub repository.

Add Tailwind/shadcn foundation, design tokens and typography.

Build the reusable EMS sidebar, header, mobile navigation and page container.

Configure environment variables and Supabase browser/server clients.

Create the protected-route structure and placeholder routes for final EMS modules.

Set up clean folders, lint/build conventions and error handling foundation.

Result of this phase A real EMS application runs cleanly, connects to Supabase, and has the shared shell ready for authentication and business features.

## Phase 1 is complete only when

The app builds and runs without blocking errors.

Supabase connection works through environment variables.

No service-role or secret key is exposed in browser code.

Desktop and mobile app shell are stable.

Core routes and protected-route structure are ready.

Not part of Phase 1 Employee management, scrum, attendance and requests are not built yet. They are added only after the foundation is stable.

ACCESS AND COMPANY STRUCTURE

PHASE 2  Authentication & Access

| AFTER PHASE 1 | Make login, sessions and role-based access work correctly. |
| --- | --- |

What we build

Create the demo Supabase Auth user with a simple password.

Build login and logout.

Link the Auth user to EMS-DEMO-001.

Load the employee profile and role after login.

Protect application routes.

Use one role-aware navigation configuration for Employee, Manager and Super Admin.

Verify access using real authenticated sessions and RLS.

Result of this phase The demo Super Admin can securely sign in, and application access follows the EMS permission model.

PHASE 3  Employees & Company Structure

| AFTER PHASE 2 | Turn existing organization tables into real employee-management screens. |
| --- | --- |

What we build

Employee list and employee profile.

Departments and reporting hierarchy.

Role and access assignment.

Work schedule assignment.

Employee activation and deactivation.

Prepare the real employee import workflow.

Result of this phase The system knows who each employee is, where they belong, who they report to and which role/schedule applies.

EMPLOYEE DAILY WORK

PHASE 4  My Day & Scrum

| AFTER PHASE 3 | Build the employee daily workflow from sign-in to sign-off. |
| --- | --- |

What we build

Sign in with scrum.

Previous unfinished work, carried items and backlog.

Current scrum items and progress percentages.

Obstacles and blockers.

Break and meeting actions.

Sign off with final percentages and notes.

100% closes a task; below 100% carries forward.

Sign back in without erasing earlier events.

Result of this phase An employee can complete the full My Day workflow using real Supabase data.

PHASE 5  Attendance & Live Presence

| AFTER PHASE 4 | Use the same daily events to power attendance and live team status. |
| --- | --- |

What we build

Attendance and workday calculations.

Active, Idle, Away, On Break, In Meeting, Offline and Signed Off states.

Heartbeat and current presence.

Presence history and daily timeline.

Manager Live View.

Attendance correction workflow with reason and audit history.

Result of this phase Managers see accurate live status and attendance without duplicate attendance entry.

REQUESTS AND MANAGEMENT

PHASE 6  Requests & Approvals

| AFTER PHASE 5 | Build leave, shift-change and hour-change workflows with controlled approvals. |
| --- | --- |

What we build

Employee request form and history.

Leave, Shift Change and Hour Change.

Manager approval stage.

Final approval when company settings require it.

Rejection comments and cancellation.

Leave ledger and approved schedule changes.

Notifications and audit records from trusted server workflows.

Result of this phase Requests move through the correct approval chain and update business records once.

PHASE 7  Management Dashboard & Reports

| AFTER PHASE 6 | Give managers one place to use data already produced by employee workflows. |
| --- | --- |

What we build

Team dashboard and summary cards.

Scrum board and blockers.

Manager-added scrum tasks.

Employee drill-down.

Team attendance.

Request review queue.

Scrum, attendance, hours, leave and request reports.

CSV exports.

Result of this phase Managers can run daily team operations using the same employee, scrum, attendance and request records.

ADMIN AND LAUNCH

PHASE 8  Admin, Settings & Audit

| AFTER PHASE 7 | Complete organization-wide controls for Super Admin. |
| --- | --- |

What we build

Company settings.

Schedules and holidays.

Leave types and system defaults.

Employee access control.

Import history and import errors.

Audit log.

Final administrative workflow controls.

Result of this phase Super Admin can manage organization-wide settings and review sensitive changes from one controlled admin area.

PHASE 9  Production QA & Pilot

| FINAL PHASE | Verify the complete EMS before wider company rollout. |
| --- | --- |

What we build

Employee, Manager and Super Admin end-to-end tests.

RLS and permission tests.

Refresh, browser-close, duplicate-click, auth-expiry and network edge cases.

Desktop, tablet and mobile QA.

Build, lint and performance checks.

Pilot with a small internal team.

Fix pilot issues before wider rollout.

Deactivate demo-only access before production launch.

Result of this phase The EMS is ready for controlled production rollout, not merely a visual demo.

SINGLE SOURCE OF TRUTH

# 3. Rules that prevent duplication

| Rule | Meaning |
| --- | --- |
| One database source per business fact | Do not store the same fact independently in several places unless it is an intentional historical snapshot. |
| One permission model | Supabase RLS is the real data-security layer; the UI reflects it but does not replace it. |
| One server workflow for sensitive actions | Approvals, leave balances, attendance corrections and audit writes use trusted server logic. |
| One reusable UI pattern | Repeated tables, status badges, cards, filters and modals are components, not page-by-page copies. |
| One status vocabulary | Presence, workday, scrum and request statuses are defined once and reused. |
| One settings source | Grace period, work targets and approval rules come from company settings. |
| One backend | The existing Supabase project is the canonical backend; we do not create a second temporary backend. |

CURRENT POSITION: PHASE 1 - PROJECT FOUNDATION The backend preparation is complete enough to start. The next real coding work is to initialize the Next.js app in Demo-EMS-, connect Supabase and build the shared EMS shell. After Phase 1 passes its checks, we move to Phase 2 Authentication.

## Decisions to confirm later - not blocking Phase 1

Attendance correction permissions; exact leave balances; meeting-time rule; final production approval chain; holiday/weekend policy; manager scrum edit rights; employee submitted-scrum edit rights.